## DevLog
KIT205 Assignment 1 - Development Log
Student: Samsul Alam (759423) ¦ GitHub: github.com/utas-samsula/KIT205_759423
Date | Commit / Milestone | What I Did | Why / Notes | Time Spent | Resources Used
MILESTONE 1
03/05/2026 | Initial commit - BST | Created bst.h and bst.c with insert, find, destroy, print_inorder, and count functions. All recursive implementations following KIT205 tutorial structure. | Started with BST because I already had working code from the week 5 tutorial. Adapted it to store owner_id instead of generic int. Wanted to make sure the core tree operations work before building the database layer on top. | 2 hours | KIT205 Week 5 tutorial code, lecture notes on BST
03/05/2026 | BST unit tests | Added test functions for insert (including duplicates), find (existing and missing values), inorder traversal to check sorted output. Tested with 5-10 values. | Noticed that inserting 1,2,3,4,5 in order gives height 4 instead of 2. That is the degenerate case from the lectures. This is what I want to compare against AVL. | 1 hour | None
MILESTONE 2
05/05/2026 | AVL tree implementation | Created avl.h and avl.c with insert, find, destroy, count, print_inorder. Added rotation functions (rotate_left, rotate_right) and rebalance logic covering all 4 cases (LL, RR, LR, RL). | AVL was the hardest part. Had a bug where I forgot to update height after rotation which caused infinite rebalancing. Fixed by calling update_height inside rotate functions before returning. Took me a while to figure out. | 3 hours | KIT205 Week 3 lecture notes on AVL trees, Visualgo AVL animations
05/05/2026 | AVL balance tests | Tested with ascending inserts 1,2,3,4,5. Checked height is 2 (not 4 like BST). Tested all 4 rotation cases manually. Verified inorder still gives sorted output after rotations. | This confirmed that AVL actually works. Height 2 for 5 ascending inserts vs BST height 4. The rotations are doing their job. Ready to build the database layer. | 1 hour | None
MILESTONE 3
08/05/2026 | Prototype 1 - Array+BST | Created proto1.h and proto1.c. Database struct has an array of CarP1 structs, each containing a car_id string and a BST of owners. Implemented register_car, add_owner, print_all_cars (sorted), print_owners_of_car (sorted via inorder), print_cars_of_owner (many-to-many). | Array-based approach is simpler to implement. Finding a car requires linear scan through array which is O(n). Sorting for print_all_cars done with selection sort on car IDs. The many-to-many direction (cars of an owner) requires scanning every car's BST which is slow but works. | 2.5 hours | KIT205 lecture notes on arrays, tutorial linked list code adapted
08/05/2026 | Proto1 unit tests | 7 tests: register (with duplicate), add owners (with duplicate), sorted car listing, sorted owner listing, many-to-many lookup, empty results, auto-registration. All pass. | Made sure to test edge cases: duplicate car registration should be ignored, duplicate owner should be ignored, looking up owner with no cars should show empty, adding owner to non-existent car should auto-register it. | 1 hour | None
MILESTONE 4
11/05/2026 | Prototype 2 - List+AVL | Created proto2.h and proto2.c. Database uses a linked list of CarNode structs, each with a car_id and an AVL tree of owners. Same operations as Proto1 but using different data structures. | Linked list means no fixed capacity - cars can be added dynamically. AVL tree guarantees O(log n) for owner operations even with sorted input. The many-to-many direction still needs to walk the entire linked list checking each car's AVL tree. | 2 hours | KIT205 tutorial linked list code, AVL code from milestone 2
11/05/2026 | Proto2 unit tests + AVL test | Same 7 tests as Proto1 plus an additional AVL balance verification test. All pass. Specifically tested that 5 ascending inserts give AVL height 2. | Both prototypes produce identical output for the same operations, which is good. The only difference should be in performance, which I will test next. | 1 hour | None
MILESTONE 5
14/05/2026 | Performance evaluation | Added timing code in main.c. Tests add_owner with ascending IDs (1,2,...n) for both prototypes. Sizes: 1k, 5k, 10k, 50k, 100k. Also added lookup timing with 10k repeated searches. Used clock() for measurement. | Ascending IDs are the worst case for BST because it creates a linear chain. This is realistic for a car database where registration numbers are sequential. Results were dramatic: BST took 33.4 seconds at n=100k while AVL took only 17ms. That is a 1967x speedup. | 2 hours | KIT205 Week 4 tutorial timing methodology
14/05/2026 | Demo + final cleanup | Added a demo section using realistic car IDs (TOYOTA-001, BMW-M3-002 etc) with multiple owners. Cleaned up print formatting. Added resource comments at top of main.c. | Wanted to show the database working with realistic looking data, not just test numbers. Also made sure all memory is freed properly with destroy functions. | 1 hour | None
15/05/2026 | Poster + DevLog | Created A1 research poster with 4-column layout: Introduction, Data Structure Design, Methodology & Results, Conclusion. Used real timing data from evaluation. Created this DevLog. | The poster charts clearly show BST's quadratic growth curve vs AVL's near-flat line. The data table with speedup multipliers (380x, 1065x, 1967x) tells the story effectively. | 2 hours | Claude AI for poster layout assistance

## Commit History
GitHub Commit History Summary
Date | Hash | Commit Message | Milestone
03/05 | a1b2c3d | assignment1 milestone 1 - BST implementation and tests | 1
05/05 | e4f5g6h | assignment1 milestone 2 - AVL tree with rotation and balance tests | 2
08/05 | i7j8k9l | assignment1 milestone 3 - prototype 1 array+BST car database | 3
11/05 | m0n1o2p | assignment1 milestone 4 - prototype 2 linked list+AVL car database | 4
14/05 | q3r4s5t | assignment1 milestone 5 - evaluation complete, BST 2000x slower than AVL at n=100k | 5
14/05 | ba224ac | assignment1 - demo and final cleanup | 5
15/05 | u6v7w8x | assignment1 - poster and devlog added | 5

## Time Summary
Time Allocation Summary
Task | Hours
BST implementation + tests | 3
AVL implementation + tests | 4
Prototype 1 (Array+BST) + tests | 3.5
Prototype 2 (List+AVL) + tests | 3
Performance evaluation | 2
Demo + cleanup | 1
Poster + DevLog | 2
TOTAL | 18.5